## SEP Gantt chart
| Colour coding: | Milestones |  | Assessments
|  | Due dates |  |  | September |  |  |  |  | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June
|  | Assessments |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Winter vacation Wk 1 | [6 empty] | Winter vacation Wk 2 | [6 empty] | Winter vacation Wk 3 | [6 empty] | Assessments Wk 1 | [6 empty] | Assessments Wk 2 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Spring vacation Wk 1 | [6 empty] | Spring vacation Wk 2 | [6 empty] | Spring vacation Wk 3 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 (revision week) | [6 empty] | Assessments Week 1 | [6 empty] | Assessments Week 2 | [5 empty] | Assessments Week 3
[5 empty] | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
Task ID | Category | Task | Lead | % done
1.1 | Client liaison | Contact client to arrange first meeting | Kaushiki | 100% | bar: Week 2 3
1.2 | Client liaison | Research client | ALL | 100% | bar: Week 2 3 to Week 2 4
1.3 | Client liaison | Plan agenda for first meeting and key questions to answer | ALL | 100% | bar: Week 2 3 to Week 2 4
1.4 | Client liaison | Take notes during meeting and send to all attendees | Wren | 100%
1.5 | Client liaison | Add client key dates to Gantt chart | ALL | 100%
1.6 | Client liaison | Meet client every 2 weeks on Thursday | ALL | 100%
2.1 | Project planning | Arrange time and place group will work together and how you will communicate | ALL | 100% | bar: Week 2 3
2.2 | Project planning | Arrange to meet your mentor | ALL | 100% | bar: Week 2 3
2.3 | Project planning | Add key dates to your Outlook calendars, Gantt Chart and project descriptions | Kaushiki | 100% | bar: Week 2 6
2.4 | Project planning | Set up team communication channels | ALL | 100% | bar: Week 2 3
3.1 | Project management | Read client's request and send signed contract to client | ALL | 100% | bar: Week 3 10 to Week 3 16
3.2 | Project management | Identify Stakeholders, User Stories | ALL | 100% | bar: Week 2 5 to Week 2 9
3.3 | Project management | Choose liecence | ALL | 100% | bar: Week 2 5 to Week 3 13
3.4 | Project management | Peer Presentation | ALL | 100% | bar: Week 7 9 to Week 7 13
3,5 | Project management | GitHub workflow for CI/CD | Wren | 100% | bar: Week 16 13 to Week 20 19
3.6 | Project management | GitHub workflow for issue templete | Haixin | 100% | bar: Week 16 17
3.7 | Project management | Beta Release | ALL | 100% | bar: Week 16 16
4.1 | UI design | Constructing the frameworks | Haixin,Wren | 100% | bar: Week 3 10 to Week 4 23
4.2 | UI design | Design the questionnaire page | Wren | 100% | bar: Week 5 24 to Week 6 6
4.3 | UI design | Design the spalsh screen | Haixin,Wren | 100% | bar: Week 7 7 to Week 8 20
4.4 | UI design | Decide to uniform the interface color | Haixin,Wren | 100% | bar: Week 10 1 to Week 10 4
4.5 | UI design | Design the slide button and progress bar | Haixin,Wren | 100% | bar: Week 5 27; Week 13 27 to Week 13 28; Week 14 3 to Week 15 9
5.1 | Questionnaire | Consent | Wren | 100% | bar: Week 7 10 to Week 7 11
5.2 | Questionnaire | Prolific ID page | Haixin | 100% | bar: Week 14 5 to Week 15 12
5.3 | Questionnaire | Questionnaire 1-16 | Haixin,Wren | 100% | bar: Week 7 11 to Week 11 5; Week 15 10 to Week 15 12
5.4 | Questionnaire | Disable the page back navigation | Haixin | 100% | bar: Week 10 1 to Week 11 5
5.5 | Questionnaire | Game instructions | Wren | 100% | bar: Week 14 5
5.6 | Questionnaire | Progress bar and slide button | Haixin,Wren | 100% | bar: Week 13 27 to Week 14 2; Week 15 10 to Week 16 16
5.7 | Questionnaire | Finished Questions and exit page | Haixin,Yichen | 100% | bar: Week 17 26 to Week 20 13
6.1 | Game | Game map 1 and Game map 2 | Haixin,Yichen,Chongqi | 100% | bar: Week 15 10 to Week 17 25; Week 19 6 to Week 19 9
6.2 | Game | Score bar | Haixin | 100% | bar: Week 15 10 to Week 17 20
6.3 | Game | Pacman eat pellets | Haixin | 100% | bar: Week 18 4 to Week 19 10
6.4 | Game | Pacman movement | Haixin | 100% | bar: Week 16 18 to Week 18 27
6.5 | Game | Guess box | Chongqi,Haixin | 100% | bar: Week 19 6 to Week 19 12
6.6 | Game | Counting score | Chongqi | 100% | bar: Week 19 6 to Week 19 12
6.7 | Game | Jump page from level 1 to level 2 | Haixin | 100% | bar: Week 20 17 to Week 21 20
6.8 | Game | Click button rearrenge | Chongqi | 100% | bar: Spring vacation Wk 3 13 to Week 23 27
6.9 | Game | Game logic | Haixin | 100% | bar: Week 21 23 to Week 23 27
7.1 | Database | Use fireabse to store the questionnaire answer | Wren | 100% | bar: Week 15 8 to Week 15 9
7.2 | Database | Use firebase to store game score | Wren | 100% | bar: Week 20 17 to Week 23 28
8.1 | Others | Code comments | Haixin,Yichen,Chongqi | 100% | bar: Week 23 28 to Week 23 30
Note on DG3: Sarah Connolly: Some time in the 2 week assessment period: exams for Algorithms II, Computer Systems A and Programming Languages & Computation
Note on IC3: Sarah Connolly: Connolly:Sometime in the 3 week Assessment period: exams for Data-Driven Computer Science and Computer Systems B
Note on O4: Sarah Connolly: First client meeting First mentor meeting
Note on BJ4: Sarah Connolly: Project presentations in these 2 weeks
Note on BT4: Sarah Connolly: Computer Systems A coursework due date
Note on BX4: Minimum Viable Product Release
Note on ER4: Sarah Connolly: Deploy Beta version
Note on FR4: Sarah Connolly: Porject Presentations to staff in this fortnight
Note on HO4: Sarah Connolly: Deploy Final Version release
Note on HR4: Sarah Connolly: SEP Project Presentation and Demo
Note on HT4: Sarah Connolly: Interaction & Society Coursework due date